## Latest report
Damco Foundation completion review
Updated 08 Oct 2026. Includes 8 missed fixes and all 26 screenshot/attachment requests. Open rows require physical acceptance.
Implemented means source fix present. DOM/model checks do not certify browser layout, real assistive technology or recipient rendering.
Passed: 65 regression tests; 3,880 DOM assertions; 817 defined combinations; 131 component pages plus Patterns/Templates. All 634 default token properties import in both modes.
|  |  |  | Rows implemented | 47 |  | Open follow-up rows | 12
ID | Section | Current status | Priority | Problem | Solution | Task / guide | Reference | Current evidence
F01 | Shared prompts | Implemented | P1 | Prompts lacked the full current configuration; inherited changes could be unclear. | Add applied settings, current tokens, theme, unit, density and direction to local Markdown. | Edit a setting → inspect Current Foundation configuration → copy → compare values. | foundation-runtime.js, experience.js | Foundation sweep plus all 133 library pages pass current-context and changed-setting prompt checks.
F02 | Copy Markdown | Implemented | P1 | Copy could report success without copying. | Share a clipboard helper; support a successful fallback; show manual-copy guidance on failure. | Test normal copy, denied permission, missing API and failed fallback. | shell.js, local Foundation renderers | Foundation copy checks and all 133 library pages pass real script success/failure paths; no rendered browser claim.
F03 | Typography reset | Implemented | P1 | A failed reset could leave persistence disabled. Later edits stopped saving. | Enable reset suppression only after removal succeeds. | Block reset → edit a weight → allow storage → save and reload. | typography.js, reset handler | Failed reset followed by successful save is covered by saved recovery checks.
F04 | Typography input / fonts | Implemented | P1 | Empty tracking could become zero. Pending uploads could undo reset. | Keep empty tracking invalid; cancel pending uploads; clear old assets on reset. | Clear tracking → previous applied value remains → enter a valid value. Upload → reset before completion. | typography.js, tracking / upload handlers | Blank tracking and font read/load/reset races covered in DOM checks. Real font decoding remains pending.
F05 | Icon references | Implemented | P1 | References disappeared after reload; no removal or read-error feedback. | Persist assets; restore thumbnails; add removal, keyboard access, limits and read errors. | Upload → save → reload → remove → reload. Test unsupported and oversized files. | icons.js, reference upload | Upload, removal, reload, reset and read-error checks pass in DOM. Rendered assets remain pending.
F06 | Icon geometry | Implemented | P1 | Isometric/3D ignored selected size. SVG stroke was incorrectly described as px. | Apply width/height to every style. Document intrinsic viewBox and unitless SVG stroke. | Select each style and size; compare SVG dimensions, saved values and Markdown. | icons.js, preview; icons.html, stroke guidance | 112 defined icon cases pass. SVG width/height and unit guidance checked. Optical rendering remains pending.
F07 | Borders validation | Implemented | P1 | Invalid drafts could reach persistence. Zero width/opacity was ignored on reload. | Validate hex and opacity; preserve zero values when restoring. | Try incomplete hex and opacity 101; then save width 0 / opacity 0 and reload. | borders.js, validation / reload | Invalid hex/opacity and zero-value reload pass in saved DOM checks.
F08 | Grid validation | Implemented | P1 | Invalid recommended grids were only flagged when Custom was selected. | Validate columns/gutter for every grid type; keep invalid drafts unsaved. | Enter 25 columns or a fractional gutter; check validation and previous applied grid. | grid-layout.js, numeric editor | Numeric bounds and 96 defined grid cases pass in saved DOM checks.
F09 | Data Format | Implemented | P1 | Prompts updated only after change/blur. Blank numbers and simultaneous errors were unclear. | Commit valid input events; reject invalid values; identify every invalid field together. | Edit without blur; test blank decimals, invalid zone, two-character mask and comma-decimal conflict. | data-format.js, configuration form | 24 controls, live updates, 48 locale combinations and simultaneous errors checked in DOM.
F10 | AI action colors | Implemented | P1 | Approve/Reject referenced missing tokens and could lose text contrast on custom surfaces. | Derive semantic colors and separate default/hover/active backgrounds and text colors. | Test light/dark, varied status colors and panel backgrounds; compare every state. | foundation-model.js, shell.css | Fresh model tests pass for both themes, custom surfaces and all action states.
F11 | Color contrast readouts | Implemented | P1 | Brand readouts used a different foreground rule; surfaces checked fixed text defaults. | Use the shared state foreground rule and current Typography colors. | Change brand or primary text color; compare contrast readouts with resolved tokens. | foundations.js, contrast readouts | Source uses shared foreground/current text colors. Fresh contrast model tests pass. Rendered labels pending.
F12 | Dark customization | Implemented | P2 | Opening separate dark customization was not represented durably in the prompt. | Save and restore the edit-enabled choice independently of auto-generated color state. | Toggle dark customization → copy → reload → confirm choice. | foundations.js, dark controls | Saved DOM checks cover toggle persistence and prompt state.
F13 | Shared sizing | Implemented | P2 | No direct reset for shared sizing; icon precedence unclear. | Add Reset shared sizing and explain fallback versus explicit icon/component sizing. | Change sizing → reset → reload. Block storage and confirm failed reset preserves values. | foundation-runtime.js, Shared sizing | Saved recovery checks cover successful and failed shared-sizing reset.
F14 | Shadows / AI exports | Implemented | P2 | No local Markdown export. | Add local exports with current recipes and tokens, including px/rem references. | Change shadow philosophy / inherited status color → copy current Markdown. | shadows.html, ai-foundation.html | Saved DOM checks cover both local exports and live context. Recipient rendering remains pending.
F15 | AI example actions | Implemented | P1 | Examples implied real saved changes and cited unverified file evidence. | Label demonstrations; remove fabricated evidence; restore focus through result/Undo. | Approve / Reject → read honest result → Undo → confirm focus and restored actions. | ai-foundation.js, ai-foundation.html | Saved DOM checks cover honest results, Undo and focus restoration. Screen-reader acceptance pending.
F16 | Accessibility documentation | Implemented | P2 | Guidance still described settings as export-only; counts and migration claims were stale. | Document current live application, copy errors, reset behavior, targets and migration limits. | Compare state-model descriptions with the actual editor and failure tests. | accessibility.html | Universal record versions, recovery and current live state are documented. Assistive-technology acceptance remains open.
F17 | Guidelines / Copywriting layout | Implemented; visual pending | P2 | Three-part reference rows inherited four-column layouts; Read More could shift adjacent values. | Wrap descriptions; use three columns with responsive stacking and consistent panel gaps. | Check description expansion, separators and column alignment at narrow/wide widths in a browser. | guidelines.html, copywriting.html, foundation.css | Three-column CSS and description wrapper present. Width, wrapping and alignment require browser checks.
R01 | All pages / browser | Verification pending | P1 | Rendered gutters, padding, dropdowns and bottom scrolling have not been checked. | Complete browser acceptance. Fix any reproduced layout defect. | Test all 14 pages at 320, 375, 768, 1024 and 1440 px. Check equal side gutters, dropdowns, banner dismissal and scroll bottom. | Latest report: Remaining tasks / Browser. shell.css; experience.css; foundation.css | Browser connection retry returned no available browser on 08 Oct. DOM does not measure rendered layout.
R02 | Accessibility | Verification pending | P1 | Real keyboard, assistive technology, zoom and forced-color behavior remain unverified. | Complete accessibility acceptance and record results. | Tab through controls. Check announcements, error focus, 200% zoom, forced colors and four-line Read More / Read Less. | Latest report: Remaining tasks / Accessibility. accessibility.html; foundation-runtime.js | DOM focus and state checks pass. No real screen-reader or rendered-browser acceptance evidence.
R03 | Fonts / assets | Verification pending | P1 | DOM tests simulate FontFace. Real decoding, remote loading and rendered assets remain unverified. | Test real font and asset loading, failure and fallback. | Upload valid/invalid fonts. Block remote fonts. Reload. Check weights, fallback, SVG/raster references and unsupported files. | Latest report: Remaining tasks / Fonts/assets. typography.js; icons.js | Read/load failure and stale-upload logic tested in DOM. Real renderer still required.
R04 | Export integration | Verification pending | P1 | Copied recipes have not been rendered in a separate recipient application. | Standalone recipient fixture, validated Foundation import and token-parity checks are implemented; rendered comparison remains open. | Load Export Foundation JSON into audit/recipient-fixture.html. Compare themes, units, roles, fonts, assets and states. | audit/recipient-fixture.html; foundation-import.js; tests/foundation-release.test.cjs | Model and integrated DOM recipient token parity pass. Real recipient painting and copied component recipes still require browser evidence.
R05 | Settings migration | Implemented | P2 | Foundation editors lack one consistent versioned-record migration framework. | Shared schemaVersion 1 migration, validation, future/malformed record preservation, backup and explicit reset. | Run the 15-schema recovery cases; check reset then subsequent save. | foundation-model.js; shell.js; foundation-runtime.js; audit/pending-tasks-2026-10-08.json | All 15 schemas pass integrated future-record preservation, reset and subsequent save; legacy model fixtures pass.
R06 | Original audit backlog | Partial | P1 | The latest functional pass does not close all 100 original requirements. | Generated section contracts, model/source fixes and full 100-ID reconciliation are saved. | Complete the 14 acceptance-pending original findings using a real browser, assets and assistive technology. | foundation-pending-task-completion-2026-10-08.md; audit/foundation-task-status-2026-10-08.json | 86 source/documentation requirements implemented; 14 remain Partial because acceptance evidence is unavailable. No rendered checks are closed.
N01 | Borders state documentation | Implemented | P1 | Documentation promises independently editable width, opacity and style. State rows expose fixed geometry and color editors. | Label state geometry fixed; distinguish editable base recipe and per-state colors. Correct live-application guidance. | Compare state rows with Implementation contract and copied configuration. | borders.html:425; borders.html:426; borders.js | Source corrected in borders.html. Full DOM save, copy and border matrix pass.
N02 | Shadows state example | Implemented | P2 | Interactive-card preview labels pressed XS but the third example uses --shadow-sm. | Pressed uses --shadow-xs; button XS also corrected. Static bordered/elevated/interactive cards now have explicit recipes. | Compare SM → MD → XS. Verify rendered elevation in the browser acceptance pass. | shadows.html:328 | Source corrected in shadows.html; runtime shadow model/import and local export checks pass.
N03 | Library copy failure | Implemented | P1 | 65 page drivers reported Copied even when clipboard and fallback failed. | Shared awaited copy feedback checks actual success and announces manual-copy recovery. | Copy with normal API, denied API and failing/successful legacy fallback; preserve focus. | shell.js; all component detail scripts; patterns.js; templates.js | 131 component pages plus Patterns/Templates pass copy success/failure/focus paths.
N04 | Copied component context | Implemented | P1 | Component/pattern/template prompts missed current settings and dimension equivalence. | Prepare page Markdown with current applied snapshot and both units; keep code outputs valid code. | Change Spacing then copy each prompt; compare applied setting and px/rem values. | foundation-runtime.js; component detail scripts; patterns.js; templates.js | Each of 133 library pages passed a changed-setting prompt check.
N05 | Splitter live interactions | Implemented | P1 | Divider was pointer-only with no min panes, saved ratio or cancellation recovery. | Accessible separator controller, RTL/vertical keyboard, collapse/restore, physical minima, pointer cancel and versioned persistence. | Arrow/Shift/Home/End/Enter; cancel pointer; reload width; future record; failed reset then retry. | splitter-runtime.js; splitter-detail.js; splitter-default.html | Actual page-script interaction, bounds, save, reset and future-record scenarios pass; physical drag layout pending.
N06 | Responsive layout patterns | Implemented | P1 | Eight patterns lacked buildable transitions; Master-Detail had no working state/focus example. | Per-pattern contracts plus executable selected/empty/loading/error/retry/back example and stale-request protection. | Select record, Back, retry error, clear during load, cross narrow/wide threshold. | layout-patterns.js; foundation-contract.json; grid-layout.html | Simulated media transitions, list position, focus return, loading/error and stale cancellation pass.
N07 | Data value edge cases | Implemented | P1 | IDs/phones formatted as quantities, dates aligned as numbers, Unicode masks split characters and invalid ranges leaked. | Protect identity labels/leading zeros; numeric-only alignment; code-point masks; ordered valid ranges. | Format IDs, phone, boolean/blank number, date-only values, reverse range and emoji masks. | foundation-model.js; foundation-runtime.js; tests/foundation-followup.test.cjs | Model fixtures and actual table value/alignment checks pass.
N08 | Header icon hover | Implemented | P1 | Header default and hover mapped to the same text color. | Hover Brand and active pressed Brand apply to icon-only header controls. | Hover settings/theme/navigation and banner actions; verify currentColor paths/masks. | foundation.css; experience.css | Different state tokens are present; real hover painting still needs browser.
N09 | Contrast pill foregrounds | Implemented | P1 | 12px status pills could be unreadable on their own tinted backgrounds. | Derive foreground/background pairs with at least 4.5:1, retaining 12px Regular. | Check pass/fail pairs in both themes and white/dark/blue panels. | foundation-model.js; foundation.css; tests/foundation-followup.test.cjs | Custom/default panel contrast fixtures pass.
N10 | Incomplete typed token publish | Implemented | P1 | Published token file omitted runtime semantic roles and metrics. | Generate from the shared default resolver, both themes, with source/model/contract freshness. | Independent import; compare all property names and representative values; reject invalid/cyclic inputs. | tools/generate_tokens.py; tools/dtcg-import.cjs; tests/foundation-release.test.cjs | 613 typed tokens + 21 explicit CSS-only keywords restore all 634 default properties in each mode.
U01 | Foundation audit and task report | Implemented | P1 | Earlier tracker did not show each original finding separately. | Retain all 100 findings and their own source references; keep 14 acceptance rows open. | Filter Original findings; compare ID, current evidence and remaining task. | foundation-audit-report-2026-10-05.md; audit/foundation-finding-evidence-2026-10-08.json | 100 unique IDs, problems, recommendations and historical statuses retained.
U02 | Blue structural boundaries | Partial | P1 | Brand-colored borders appeared on page containers and sections. | Structural panels use neutral line tokens; focus/selected specimens retain semantic treatment. | Inspect unfocused containers, then keyboard focus, in both themes and custom Brand. | foundation.css; shell.css; foundation-model.js | Source distinguishes neutral containers from focus/state tokens. Real screenshot comparison still required.
U03 | Inner input strokes | Partial | P1 | Text inside composite fields gained a second border. | Composite wrapper owns border/focus; inner input border is zero. | Check outlined/filled/underlined Input, Password, Number and Search in every state. | foundation.css:50; input-detail.js | Composite CSS reset is present. Actual native field rendering remains pending.
U04 | Page and sidebar spacing | Partial | P1 | Margins, gutters, section gaps and side spacing were unequal. | Shared logical gutters, stable mirrored scrollbar space and one owner per section gap. | Measure both content edges and sidebar in wide/narrow widths; expand content and retest. | foundation.css:18; foundation.css:171; shell.css | Shared source rules present; computed box geometry needs a connected renderer.
U05 | Dropdown alignment | Partial | P1 | Unit and other dropdowns did not align with adjacent fields. | Consistent control height, padding and arrow inset; responsive minimum widths. | Compare select/input baseline and bounds at 320/375/768/1440px. | foundation.css:74; shell.css:1227 | Control CSS and DOM interaction pass; native popup placement requires browser verification.
U06 | H1-H6, Body and Paragraph | Implemented | P1 | Section headings were larger than page titles and used conflicting sizes. | Restore standard H1-H6 defaults and bind every role metric to shared tokens. | Reset Typography; inspect hierarchy; change size, weight, line height, tracking and color. | foundation-model.js; foundation.css:5; tests/foundation-typography.test.cjs | Role resolution, legacy migration, metric bindings and editor option checks pass. Visual release acceptance remains separate.
U07 | Default Inter and live typography | Implemented | P1 | Selected font and typography values did not propagate across the design. | Default headings/body use Inter; live shared resolver applies family and every role metric. | Change font; navigate; reload; inspect exported source/assets and copied current context. | foundation-runtime.js; typography.js; foundation-defaults.json | Model/DOM bindings and durable settings pass. Real font decoding is an open asset check.
U08 | 11px Caption descriptions | Implemented | P1 | Contrast labels and metadata used oversized body copy. | Caption metadata follows the 11px default Caption role and full role metrics. | Inspect contrast descriptions, RGB readouts, eyebrows and helpers; test Caption customization. | foundation.css:217; foundation.css:234; foundation-model.js | All metadata bindings use Caption metrics; rendered sizing remains part of acceptance.
U09 | 12px Regular pills | Implemented | P1 | Contrast pills needed 12px Regular typography. | Contrast tags use 12px, weight 400, with readable own-background pass/fail foregrounds. | Inspect AA/AAA and Non-text 3:1 pills in light/dark and custom panels. | shell.css:891; foundation.css; tests/foundation-followup.test.cjs | 12px/400 source binding and 4.5:1 default/custom panel model checks pass.
U10 | Four-line Read More/Less | Partial | P1 | Long descriptions expanded too far and toggles appeared inconsistently. | Measure prose overflow against four line heights; only overflowing content gets an accessible expand/collapse button. | Check 3/4/5-line prose, resize, expand/collapse, keyboard and text-spacing overrides. | foundation-runtime.js:210; foundation.css:163 | Four-line measurement/clamp and retained expansion implemented; actual line wrapping cannot be certified in jsdom.
U11 | Tabs into Group Button | Implemented | P1 | Section tabs used unjoined underlined links. | Joined Outlined Group Button tracks with active state, focus and keyboard behavior. | Click every section and Human/Machine choice; use arrows/Home/End; check overflow track. | experience.js; foundation.css:242; experience.css:5 | Group navigation regression tests and 14-page section/view checks pass.
U12 | Letter-spacing field height | Implemented | P1 | Tracking input did not match neighboring typography fields. | One shared type-editor control height applies to input and unit select. | Compare tracking, line-height, font and size fields after unit/font changes. | foundation.css:83; shell.css:1227 | Identical height, box sizing, typography and border recipe present; rendered geometry pending.
U13 | Gap between tracking/unit fields | Implemented | P1 | Paired tracking and unit fields used a different gap. | Tracking pair uses the same 16px spacing token, flexible numeric width and bounded select. | Compare paired input gap with adjacent editor columns at multiple widths. | shell.css:1230 | Specific tracking selector uses --space-16; shared 4px wrapper rule does not override its higher specificity.
U14 | px/rem relevance and interaction | Implemented | P1 | Unit selection failed and was shown on unrelated pages. | Working shared radios/paired controls; toolbar unit choice appears on seven dimensional Foundations. | Switch px/rem on Typography, Grid, Spacing, Radius, Borders, Shadows, Icons; inspect conversion/save/copy. | foundation-runtime.js:8; tests/foundation-units.test.cjs | Both units and 224 theme/unit/density/direction cases pass. Colors/AI/Guidelines do not get irrelevant unit selectors.
U15 | Right-aligned Foundation JSON export | Implemented | P1 | Export Foundation JSON stayed beside the unit labels. | Auto start margin sends export to the right; narrow layouts wrap within available width. | Inspect toolbar with and without unit selector; narrow width and long labels. | foundation.css:64 | Responsive flex rule present. Current JSON export passed on all nine Foundations.
U16 | px and rem in Markdown | Implemented | P1 | Copied prompts omitted equivalent rem values. | Dimensional prompts show both units; component, pattern and template prompts include current Foundation settings. | Switch units; copy prompt; compare dimensions and current applied settings. | foundation-model.js; foundation-runtime.js; all 63 component detail scripts | All 131 component pages plus Patterns/Templates pass both-unit and changed-setting copy checks.
U17 | Consistent section/banner radius | Implemented | P1 | Project banner radius differed from other sections. | Banner, panels, action buttons and joined groups use their matching semantic radius role. | Change radius philosophy; compare banner/panel outer corners and inner controls. | experience.css:8; foundation.css; radius.js | Shared --radius-md role bindings and numeric-versus-semantic radius tests pass; pixel comparison pending.
U18 | Edit icon-only/right/Google | Implemented | P1 | Edit setup text CTA and icon placement/style did not match requested design. | Use named Google Material edit icon, icon-only accessible CTA after Export on the right. | Inspect accessible name, SVG provenance, ordering and activation. | experience.js; experience.css:11; icon-catalog.json | Reviewed licensed edit path, accessible name and DOM ordering are present.
U19 | Icon-only hover color | Implemented | P1 | Header icons hovered to their unchanged default foreground. | Topbar icons and banner actions change to Brand on hover; active uses pressed Brand. | Hover theme/settings/edit/close; check SVG/mask currentColor in both themes. | foundation.css:262; experience.css:13 | Previously equal default/hover token fixed; currentColor icon source retained. Physical hover rendering pending.
U20 | Floating banner and Close | Implemented | P1 | Project context needed floating behavior and dismissal. | Sticky context banner includes Close, restores focus and updates sticky scroll offset. | Scroll content, close banner, navigate/reopen context and check focus/section reachability. | experience.js; experience.css:9 | Sticky banner, explicit close state and context-height updates are present; scroll painting needs browser.
U21 | Blank space at scroll bottom | Partial | P1 | Scrolling exposed excess page tail/blank space. | Viewport-bounded shell; main/sidebar scroll inside minmax row; consistent bottom padding; no elastic outer tail. | Scroll every page to bottom at desktop/mobile and resize; check final content/actions remain reachable. | foundation.css:175 | Shell height/min-height/overscroll and terminal section margin fixes present; physical scroll check still open.
U22 | Data Format alignment and controls | Implemented | P1 | Categories lacked customization; numeric values and rows aligned inconsistently. | All 24 controls apply current formats; three-column rows and grouped separators; protect IDs/phones; date/range/Unicode recovery. | Edit each format, save/reload/copy; test empty/loading/masked/escaped/date/number examples and invalid boundaries. | data-format.js; foundation-runtime.js:84; foundation.css:97 | 59 edits, all offered options, 48 locale/separator/group cases and identity/alignment scenarios pass. Visual column acceptance pending.
U23 | Accessibility gutters/separators | Partial | P1 | Reference rows had wrong columns and inconsistent spacing. | Three-column documentation layout, responsive stacking, protected description expansion and neutral separators. | Expand each description; inspect status alignment and panel/row gaps at narrow/wide widths. | foundation.css:133; accessibility.html | 20 DOM checks pass; actual layout, zoom and assistive-technology checks remain pending.
U24 | All Foundation/Guidelines actions | Implemented | P1 | Inputs, views, saves, resets and copies needed full functional verification. | Exercise every offered editor option plus invalid/save/recovery paths and defined matrices; fix current-prompt propagation. | Repeat the committed DOM tools; inspect each evidence JSON and any failed row before release. | tools/audit-foundation-controls.cjs; tools/audit-foundation-recovery.cjs; tools/audit-pending-tasks.cjs | 2205 main checks, 32 recovery checks, 141 pending checks, 817 defined combinations; zero failures. Arbitrary input space is not exhaustively tested.
U25 | Required red asterisk | Implemented | P1 | Mandatory fields still allowed Required text instead of the requested marker. | Required labels use * in Foundation danger color; native required/ARIA stays programmatic; conflicting dropdown guidance corrected. | Inspect required form labels and error summary; verify one explanation of the marker. | foundation-runtime.js:295; foundation.css:62; select-dropdown.html | Shared indicator runtime and corrected guideline are present; actual announcements need AT acceptance.
U26 | Remove Optional suffix | Implemented | P1 | Optional label text cluttered non-mandatory fields. | Shared indicator normalization removes optional badges; optional identity no longer blocks Project setup. | Inspect setup/other optional fields; leave blank and complete review/save. | foundation-runtime.js:297; project-model.js | Optional marker removal and profile/identity regression checks pass.

## Original findings
Original Foundation finding review
All 100 original findings retained with individual source evidence. Latest report has 17 original fixes, release tasks, 8 missed fixes and 26 user requests. Counts overlap between sheets.
Current: 86 source/documentation requirements implemented; 14 Partial awaiting environment acceptance. The final column retains historical status.
Original reference lines belong to the 05 Oct audit and may have moved. Use finding IDs and Current evidence. Filter Partial for the 14 open acceptance rows.
ID | Section | Current status | Priority | Original problem | Original recommendation | Task / guide | Original reference | Current evidence | Status on 06 Oct
X01 | Systemwide Foundation contract | Implemented | P1 | Catalog retains removed Text colors, lacks newer Spacing defaults, Typography roles, Radius Navigation and Grid Master-Detail, and has no AI & Agents entry. | Generate catalog and docs together; fail release on stale/missing sections and include dynamic guidance explicitly. | Source/documentation fix present; include this specific requirement in release acceptance. | docs-catalog.json:413; original audit #x01-p1 | Catalog regenerated from all 157 page sources, including AI and current role guidance. Current: tools/audit_pages.py; foundation-model.js. | Partial
X02 | Systemwide Foundation contract | Implemented | P1 | Fresh setup can export an empty token object; default values, semantic aliases and effective component mappings are not resolved. | Resolve defaults plus context plus overrides into a complete snapshot with provenance and mode values. | Source/documentation fix present; include this specific requirement in release acceptance. | experience.js:230; original audit #x02-p1 | Shared resolve/export materializes default and applied settings, both themes, context and platform profiles. Current: foundation-runtime.js; foundation-model.js. | Partial
X03 | Systemwide Foundation contract | Implemented | P1 | Artifact omits current border/opacity/tracking/radius/component/AI tokens; exported monospace is Inter while current CSS uses JetBrains Mono. | Regenerate and validate during release; compare all intended public names and effective values. | Source/documentation fix present; include this specific requirement in release acceptance. | design-tokens.json:228; original audit #x03-p1 | Published defaults now include all 634 applied properties: 613 typed tokens and 21 CSS-only keywords. Current: tools/generate_tokens.py; foundation-model.js. | Implemented
X04 | Systemwide Foundation contract | Implemented | P1 | It does not specify a supported version or translate typed values/references into the published interchange shapes. | Pin published DTCG version, use typed objects and alias references, document mode extensions, validate a real importer. | Source/documentation fix present; include this specific requirement in release acceptance. | tools/generate_tokens.py:120; original audit #x04-p1 | Independent importer validates typed values and alias cycles in both modes; relative em uses an explicit extension. Current: tools/dtcg-import.cjs; foundation-model.js. | Partial
X05 | Systemwide Foundation contract | Implemented | P1 | Saved, previewed, applied and exported have different meanings across sections. | Adopt one draft/validate/commit/apply/export model or clearly separate auto-save from Apply. | Source/documentation fix present; include this specific requirement in release acceptance. | foundations.js:54; original audit #x05-p1 | Valid edits auto-apply; failed writes identify unsaved preview; reload restores durable settings. Current: shell.js; foundation-model.js. | Partial
X06 | Systemwide Foundation contract | Implemented | P1 | Write failures, malformed records and future schemas have no common recovery path; visual selection can change before a write throws. | Centralize storage validation/migration; preserve last valid state and expose recoverable errors and temporary validated export. | Source/documentation fix present; include this specific requirement in release acceptance. | grid-layout.js:112; original audit #x06-p1 | All 15 records migrate legacy values, preserve malformed/future data and support explicit reset/raw backup. Current: foundation-model.js; foundation-model.js. | Partial
X07 | Systemwide Foundation contract | Implemented | P1 | Product/system choices generally lack programmatic selected state. Native keyboard activation exists, but outcome feedback is visual. | Use radio groups or labelled toggle groups with synchronized aria-pressed; announce recommendations and outcomes. | Source/documentation fix present; include this specific requirement in release acceptance. | spacing.js:67; original audit #x07-p1 | Joined button choices expose selected state; section navigation retains anchors and keyboard handling. Current: experience.js; foundation-model.js. | Partial
X08 | Systemwide Foundation contract | Implemented | P2 | Surrounding guidance, AI Rules, conditions and examples can be omitted; scales are often prose strings. | Define versioned schemas with types/units, precedence, examples and normative rules; generate both views from them. | Source/documentation fix present; include this specific requirement in release acceptance. | experience.js:421; original audit #x08-p2 | Shared schemaVersion 1, resolver precedence and current-context handoff are documented and used. Current: foundation-contract.json; foundation-model.js. | Partial
X09 | Systemwide Foundation contract | Implemented | P2 | Spacing lacks Consumer App/AI Product recommendations; Data-Heavy labels vary; Typography uses a different platform taxonomy. | Use canonical product/platform/density context, inherited choices, explicit overrides and explained fallbacks. | Source/documentation fix present; include this specific requirement in release acceptance. | grid-layout.js:140; original audit #x09-p2 | One product/platform resolver supplies recommendations; mixed-platform handoff resolves separate profiles. Current: foundation-model.js; foundation-model.js. | Partial
X10 | Systemwide Foundation contract | Partial | P2 | No per-Foundation release contract combines responsive, accessibility, native translation and change governance evidence. | Assign token owners, compatibility/deprecation rules and section-specific acceptance checks linked to environment evidence. | Attach actual viewport, zoom, forced-color, recipient and assistive-technology release evidence. Native rendering and live external agents are separate adapters, explicitly outside this web demo. | accessibility.html:247; original audit #x10-p2 | Acceptance contract separates web scope, model evidence, renderer checks, assets and external/native adapters. Current: foundation-contract.json; foundation-model.js. | Partial
NP01 | New Project | Implemented | P1 | New Project replaces the current profile while retaining global Foundations; create/edit/duplicate/switch are not distinct operations. | Rename to Project setup until isolation exists, or use project IDs and scoped Foundation stores; expose replacement consequences. | Source/documentation fix present; include this specific requirement in release acceptance. | new-project.html:183; original audit #np01-p1 | Project setup describes one shared profile and warns before replacing existing details. Current: new-project.html; new-project.html#implementation-contract. | Implemented
NP02 | New Project | Implemented | P1 | Product changes do not reconcile existing selections; platforms do not drive mobile grid defaults; no inherited/overridden review exists. | Track recommendation provenance, review affected choices after context edits, and resolve per-platform defaults. | Source/documentation fix present; include this specific requirement in release acceptance. | grid-layout.js:160; original audit #np02-p1 | Review displays recommendation before/after changes and distinguishes retained explicit overrides. Current: experience.js; new-project.html#implementation-contract. | Partial
NP03 | New Project | Implemented | P1 | No Resume/Discard/restore-saved control or timestamp exists; stale/partial drafts mask profiles; legacy draft product values are unmigrated. | Show draft/profile provenance; offer resume/discard; validate/migrate both and retain saved baseline. | Source/documentation fix present; include this specific requirement in release acceptance. | experience.js:133; original audit #np03-p1 | Resume, Discard and Backup handle saved/draft/corrupt/future cases without injecting project names as HTML. Current: experience.js; new-project.html#implementation-contract. | Partial
NP04 | New Project | Implemented | P2 | Model accepts overlength Other values and future version 999; Other descriptions lack type guards. | Validate types/bounds/supported versions in the model; define trimming and Unicode length policy. | Source/documentation fix present; include this specific requirement in release acceptance. | project-model.js:42; original audit #np04-p2 | Other/free-text fields have model bounds; draft and review validation share the profile rules. Current: project-model.js; new-project.html#implementation-contract. | Implemented
NP05 | New Project | Implemented | P1 | Focused checkbox lacks direct error association; required status is less clear in step 1; draft-save messages replace error status while typing. | Associate group error with focused controls, add a summary, mark requirements consistently and separate save feedback from validation. | Source/documentation fix present; include this specific requirement in release acceptance. | experience.js:174; original audit #np05-p1 | Error summary links invalid fields and platform group; corrected submissions route to the invalid step. Current: experience.js; new-project.html#implementation-contract. | Implemented
NP06 | New Project | Implemented | P2 | Role mainly changes destination; no role-specific checklist or Foundation completion condition exists. | Provide role-specific tasks plus a shared readiness checklist with alternate routes. | Source/documentation fix present; include this specific requirement in release acceptance. | experience.js:207; original audit #np06-p2 | Role routes and all nine readiness rows distinguish valid/default/recovery, including AI. Current: experience.js; new-project.html#implementation-contract. | Partial
NP07 | New Project | Implemented | P2 | Deep links are discarded; completed back/forward behavior undefined; final submit checks step-2 keys before full model validation. | Use explicit wizard states; route final all-field errors to steps; retire step listeners or hash state on completion. | Source/documentation fix present; include this specific requirement in release acceptance. | experience.js:191; original audit #np07-p2 | Step/history routing, final review and invalid-step focus recovery use one setup state. Current: experience.js; new-project.html#implementation-contract. | Partial
NP08 | New Project | Partial | P2 | No soft-keyboard, long-label, translated-copy or split-window contract; bespoke radii do not consistently follow saved philosophy. | Map setup to semantic tokens; verify expansion/keyboard viewport, tablet/window sizing and reflow. | Verify setup with soft keyboard, long/localized labels, split windows and 200% zoom. | experience.css:22; original audit #np08-p2 | Responsive setup layout and long-label rules are present; rendered keyboard/zoom acceptance remains open. Current: experience.css; new-project.html#implementation-contract. | Partial
NP09 | New Project | Implemented | P1 | No complete resolved token/validation/provenance/asset manifest travels through the immediate export path. | Export resolved context/defaults/overrides, validation findings, assets and open decisions; keep identity opt-in. | Source/documentation fix present; include this specific requirement in release acceptance. | project-model.js:78; original audit #np09-p1 | Immediate handoff includes resolved defaults, portable rules, current context, asset manifest and open decisions. Current: project-model.js; new-project.html#implementation-contract. | Partial
NP10 | New Project | Implemented | P2 | Mandatory identity benefit is unclear; overlapping categories/Other/browse-return lack examples. | Make identity optional unless needed; explain requirements and add category/browse/Other decision examples. | Source/documentation fix present; include this specific requirement in release acceptance. | new-project.html:170; original audit #np10-p2 | Identity is optional; categories, Other and return/edit guidance explain context choices. Current: new-project.html; new-project.html#implementation-contract. | Partial
C01 | Colors | Implemented | P1 | Brand violates documented fallback; synchronized controls contradict per-section opt-in; local Markdown can hide persisted/applied Brand dark values. | Choose explicit auto/custom/built-in policy per family or unify it; export effective values and update copy. | Source/documentation fix present; include this specific requirement in release acceptance. | foundations.html:609; original audit #c01-p1 | Separate dark edit-enabled flags persist and appear in copied current settings; disabled dark uses documented fallback. Current: foundations.js; foundations.html#implementation-contract. | Partial
C02 | Colors | Implemented | P1 | Local mode/reset changes affect other sections visually without durable transaction; reload enables all if any stored dark record exists. | Persist explicit shared preference or truly independent choices; keep section resets local, provide separate all-colors reset/undo. | Source/documentation fix present; include this specific requirement in release acceptance. | foundations.js:924; original audit #c02-p1 | Resets are scoped to their color family; separate-dark choices restore independently. Current: foundations.js; foundations.html#implementation-contract. | Partial
C03 | Colors | Implemented | P1 | Incomplete hex values can persist; Saved can coexist with older applied CSS; rejection lacks consistent field error. | Separate drafts/last-valid state; validate complete input; commit/apply coherently with errors. | Source/documentation fix present; include this specific requirement in release acceptance. | foundations.js:547; original audit #c03-p1 | Incomplete hex is a draft error; previous valid colors stay applied and incomplete values are not saved. Current: foundations.js; foundations.html#implementation-contract. | Partial
C04 | Colors | Partial | P1 | Checker omits on-brand text, raised/panel/tint surfaces, opacity and live typography overrides; fill-only swatches evaluated as text without use scope. | Use actual effective role-specific pair matrix and compositing; state badge scope explicitly. | Compare actual rendered role/surface/tint/state pairs. Model and scoped swatch checks do not certify every component. | foundations.js:972; original audit #c04-p1 | Readouts use resolved text/action colors and composited tint pairs; actual component pair acceptance remains open. Current: foundations.js; foundations.html#implementation-contract. | Partial
C05 | Colors | Implemented | P1 | Default pair misses normal-text requirement; arbitrary light brand can worsen it; no on-brand resolver/editor. | Validate default/hover/pressed pairs; add explicit or approved contrast-safe foreground and brand acceptance criteria. | Source/documentation fix present; include this specific requirement in release acceptance. | theme.css:68; original audit #c05-p1 | Default, hover and active action foregrounds are derived for at least 4.5:1 on their actual background. Current: foundation-model.js; foundations.html#implementation-contract. | Partial
C06 | Colors | Implemented | P2 | No role-validity/perceptual-order guarantee or hierarchy constraint for highly custom colors. | Document formulas/version and role mappings; validate surface distinction and allow deliberate overrides. | Source/documentation fix present; include this specific requirement in release acceptance. | foundations.js:145; original audit #c06-p2 | Derivation, perceptual limits and custom hierarchy checks are explicit; arbitrary custom ramps are not certified. Current: foundation-contract.json; foundations.html#implementation-contract. | Partial
C07 | Colors | Implemented | P1 | Hidden legacy text overrides remain active and excluded from current Foundation export map; semantic text ownership unresolved. | Migrate/retire legacy records; define semantic text and per-level precedence; export effective text. | Source/documentation fix present; include this specific requirement in release acceptance. | shell.js:96; original audit #c07-p1 | Legacy color text overrides migrate into Typography ownership and travel in current exports. Current: foundation-model.js; foundations.html#implementation-contract. | Implemented
C08 | Colors | Implemented | P2 | Hue names misrepresent purpose; field/derived/semantic token mappings inconsistent across views. | Add semantic brand/action/text/surface aliases and compatibility mapping; show them in all views. | Source/documentation fix present; include this specific requirement in release acceptance. | shell.js:37; original audit #c08-p2 | Semantic action/status/surface aliases document compatibility hue names and authoritative role ownership. Current: foundation-contract.json; foundations.html#implementation-contract. | Partial
C09 | Colors | Implemented | P2 | No exact foreground/background/icon triplets or component examples; warning/error/info/selection/data-series distinctions incomplete. | Define status anatomy, severity and component mapping; keep data colors distinct from status semantics. | Source/documentation fix present; include this specific requirement in release acceptance. | foundations.html:362; original audit #c09-p2 | Component-specific Alert/Tag/Badge/Table/validation recipes distinguish status from selection and chart series. Current: foundations.html; foundations.html#implementation-contract. | Partial
C10 | Colors | Partial | P1 | Adjustable controls lack names/current range values; opacity non-persistence insufficiently visible; narrow positioning unverified. | Use labelled ranges/numeric alternatives, announce values, visibly explain preview-only alpha, verify focus return/clipping. | Verify picker clipping, actual range announcements, keyboard focus return and narrow positioning. | foundations.js:1172; original audit #c10-p1 | Picker controls expose names/values, keyboard increments, transient opacity and Escape focus recovery. Current: foundations.js; foundations.html#implementation-contract. | Partial
G01 | Grid & Layout | Implemented | P1 | No numeric/editor/custom schema exists; Custom is just a label. | Add validated columns/gutter/margin/container/per-breakpoint controls, or label recommendation-only; require Custom definition. | Source/documentation fix present; include this specific requirement in release acceptance. | grid-layout.html:246; original audit #g01-p1 | Custom columns/gutter bounds validate every grid type; current geometry is saved/applied/exported. Current: grid-layout.js; grid-layout.html#implementation-contract. | Partial
G02 | Grid & Layout | Partial | P1 | Canonical scale remains a follow-up; threshold ranges do not form coherent consumer contract. | Adopt justified shared scale, migrate consumers, document content-driven exceptions and test boundaries. | Measure documented breakpoint/container boundaries and compatibility exceptions in a real renderer. | grid-layout.html:219; original audit #g02-p1 | Canonical container/viewport thresholds and legacy compatibility exceptions are documented; rendered boundaries pending. Current: foundation-contract.json; grid-layout.html#implementation-contract. | Partial
G03 | Grid & Layout | Implemented | P1 | No platform/container/density precedence; Consumer App four columns regardless of desktop/native target. | Resolve product plus platform/container/density; emit per-platform profiles and conflicts transparently. | Source/documentation fix present; include this specific requirement in release acceptance. | grid-layout.js:152; original audit #g03-p1 | Platform profiles, container width, explicit overrides and density precedence resolve from shared context. Current: foundation-model.js; grid-layout.html#implementation-contract. | Partial
G04 | Grid & Layout | Implemented | P1 | No max-width/margins/spans/alignment/row/baseline/nested rules; Baseline described as overlay but selected as replacement. | Define independent axes, container/span tokens and optional baseline overlay; add executable examples. | Source/documentation fix present; include this specific requirement in release acceptance. | grid-layout.html:322; original audit #g04-p1 | Independent baseline, max width, gutters, spans, nesting, source order and row alignment have buildable rules. Current: foundation-contract.json; grid-layout.html#implementation-contract. | Partial
G05 | Grid & Layout | Implemented | P1 | Too broad for long forms, reflow, virtual keyboard, fixed actions/nested regions; truncation recovery incomplete. | Prefer reflow where appropriate; define justified regions with names/keyboard/affordances/retained actions. | Source/documentation fix present; include this specific requirement in release acceptance. | grid-layout.html:451; original audit #g05-p1 | Document scrolling, reflow, virtual keyboard, fixed actions and justified independent regions are documented. Current: foundation-contract.json; grid-layout.html#implementation-contract. | Implemented
G06 | Grid & Layout | Partial | P1 | No narrow transforms, source/focus order, selected record/back behavior or pane empty/error/loading specs. | Specify each pattern across widths/states, including reading/focus restoration. | Verify each consumer pattern at wide/narrow widths, including selected-record, empty/loading/error and focus-return states. | grid-layout.html:445; original audit #g06-p1 | All eight patterns have wide/narrow/state rules; executable Master-Detail preserves selection, Back, list position and focus. Current: layout-patterns.js; grid-layout.html#implementation-contract. | Partial
G07 | Grid & Layout | Partial | P2 | Resizable/minimum panes, persisted widths, sticky/overlay collision and content priority unspecified. | Define pane bounds/collapse/resizing, sticky containment and overlay rules; link Splitter/Affix/Table. | Verify real Splitter/Affix/Table panes, min/max resizing, keyboard, persistence and overlay collision. | grid-layout.html:427; original audit #g07-p2 | Live Splitter now supports bounds, keyboard/collapse, cancellation and versioned width persistence; overlay rules documented. Current: splitter-runtime.js; grid-layout.html#implementation-contract. | Partial
G08 | Grid & Layout | Implemented | P1 | No breakpoints/pattern/overflow rules or executable Custom geometry travel. | Export effective geometry, semantic tokens, patterns, boundaries and validation with normative guidance. | Source/documentation fix present; include this specific requirement in release acceptance. | grid-layout.js:28; original audit #g08-p1 | Layout Markdown carries effective Custom geometry, pattern rules, breakpoints and overflow guidance. Current: grid-layout.js; grid-layout.html#implementation-contract. | Partial
T01 | Typography | Implemented | P1 | Uploaded font cannot reproduce after navigation/reload or handoff; named family is insufficient. | Package durable authorized font reference/faces/install rules or visibly label preview-only. | Source/documentation fix present; include this specific requirement in release acceptance. | typography.js:163; original audit #t01-p1 | Uploaded font data and source manifest persist and travel in Foundation JSON; reset removes old runtime faces. Current: typography.js; typography.html#implementation-contract. | Implemented
T02 | Typography | Implemented | P1 | Preview can show new font while Markdown/storage retain old one until next interaction; FileReader error unhandled. | Commit/render on successful load; expose loading/retry/cancel/read/load errors, preserve prior valid font. | Source/documentation fix present; include this specific requirement in release acceptance. | typography.js:164; original audit #t02-p1 | Read/load errors, retry and generation guards prevent late fonts or reset uploads from replacing current values. Current: typography.js; typography.html#implementation-contract. | Partial
T03 | Typography | Implemented | P1 | No effective semantic typography/component resolver; application scope unclear. | Resolve semantic tokens and bindings or explicitly state export-only settings; show effective previews. | Source/documentation fix present; include this specific requirement in release acceptance. | shell.js:165; original audit #t03-p1 | Every role resolves family, size, weight, style, line height, tracking and color; shared CSS binds actual headings. Current: foundation.css; typography.html#implementation-contract. | Partial
T04 | Typography | Implemented | P1 | Interaction states treated as independent type levels; visual style confused with semantic hierarchy. | Separate text roles and state color modifiers; define Body/Paragraph and visual versus HTML headings. | Source/documentation fix present; include this specific requirement in release acceptance. | typography.html:1070; original audit #t04-p1 | Semantic heading level remains independent of visual size; status modifiers retain readable base typography. Current: foundation-contract.json; typography.html#implementation-contract. | Partial
T05 | Typography | Implemented | P1 | Very tight values allowed without guidance; clamping impedes entry; visible draft snapshot can differ from saved picker. | Validate on blur/commit, preserve draft, recommend role bounds/exceptions and actual pair checks. | Source/documentation fix present; include this specific requirement in release acceptance. | typography.js:274; original audit #t05-p1 | Full field validation preserves invalid drafts, including blank tracking, instead of silently committing zero. Current: typography.js; typography.html#implementation-contract. | Partial
T06 | Typography | Implemented | P1 | No arbitrary-scale/H2–H6/other-role adaptation or saved-platform mapping. | Define explicit responsive role tokens or approved fluid ranges plus platform/minimum rules. | Source/documentation fix present; include this specific requirement in release acceptance. | typography.html:285; original audit #t06-p1 | Standard H1-H6 restore, platform preset mapping and arbitrary customized metric export share the resolver. Current: foundation-model.js; typography.html#implementation-contract. | Partial
T07 | Typography | Partial | P1 | Actual readable roles/surfaces/scripts/spacing not demonstrated; muted defaults compute ~3.56:1 on white and ~3.21:1 on dark panel. | Verify actual text/surface roles; correct defaults or restrict uses; test expansion/scripts/text spacing. | Verify rendered scripts, expansion, user text-spacing overrides and customized text/surface pairs; default pair math passes. | typography.html:1721; original audit #t07-p1 | Default text pair checks pass; localization, text spacing and rendered custom-pair acceptance remain open. Current: tests/foundation-release.test.cjs; typography.html#implementation-contract. | Open
T08 | Typography | Partial | P2 | Load failure/unsupported faces/synthesis/variable axes/fallback metrics and file bounds unspecified. | Define valid faces, fallback/loading/hosting/axes; validate type/size and show unavailable-face states. | Verify real font decoding, network failure/retry, supported faces, synthesis and fallback metrics. | typography.js:115; original audit #t08-p2 | Font bounds, requested faces, retry, synthesis/fallback guidance are present; real decoding still pending. Current: typography.js; typography.html#implementation-contract. | Partial
T09 | Typography | Implemented | P1 | Standard button/label/table/code/link/eyebrow roles and AI Rule do not travel; assets/responsive styles incomplete. | Export semantic roles, rules, responsive variants, units and font dependencies. | Source/documentation fix present; include this specific requirement in release acceptance. | typography.js:386; original audit #t09-p1 | Button/label/table/code/link/eyebrow role mapping, font assets and responsive rules are included in handoff. Current: foundation-contract.json; typography.html#implementation-contract. | Partial
T10 | Typography | Implemented | P2 | Copy/view/category actions can write unchanged values; edited styles leave preset active; reseeding lacks visible diff/undo. | Persist real value changes only; mark modified presets Custom; review/undo multi-level changes. | Source/documentation fix present; include this specific requirement in release acceptance. | typography.js:459; original audit #t10-p2 | Preset change previews affected sizes, supports scoped Undo and retires stale preset/Undo after edits/reset. Current: typography.js; typography.html#implementation-contract. | Partial
S01 | Spacing | Implemented | P1 | No resolver/application for selected system; some advertised values lack named tokens. | Define primitive scale plus semantic role mapping per system; resolve/export, or mark advisory. | Source/documentation fix present; include this specific requirement in release acceptance. | spacing.js:107; original audit #s01-p1 | All offered spacing systems resolve applied scale and aliases, including zero and advertised values. Current: foundation-model.js; spacing.html#implementation-contract. | Open
S02 | Spacing | Implemented | P1 | Competing allowed-value contracts; zero/auto/percent/negative/fluid exceptions unspecified. | Define primitive availability, role recommendations and exceptions with precedence. | Source/documentation fix present; include this specific requirement in release acceptance. | spacing.html:344; original audit #s02-p1 | Allowed tokens and zero/auto/percent/negative/fluid exceptions are explicitly governed. Current: foundation-contract.json; spacing.html#implementation-contract. | Open
S03 | Spacing | Implemented | P1 | No exact micro/control/layout algorithm and inconsistent combined-unit mapping. | Define role/density/platform resolver and correct Cross-Platform choice; display effective results. | Source/documentation fix present; include this specific requirement in release acceptance. | spacing.html:291; original audit #s03-p1 | Adaptive micro/control/layout resolution uses a defined algorithm and consistent px/rem conversion. Current: foundation-model.js; spacing.html#implementation-contract. | Open
S04 | Spacing | Implemented | P2 | Common setup types silently fall back; duplicated platform/product suggestions vary. | Canonical taxonomy, explained fallback, supported Consumer/AI defaults. | Source/documentation fix present; include this specific requirement in release acceptance. | spacing.js:136; original audit #s04-p2 | Shared project taxonomy and context mappings replace contradictory per-page recommendations. Current: foundation-model.js; spacing.html#implementation-contract. | Implemented
S05 | Spacing | Implemented | P2 | Exact label/helper/error/group/list/toolbar/empty/wrapped spacing incomplete; scrim versus content padding ambiguous. | Define semantic relationship tokens and complete composition/state examples. | Source/documentation fix present; include this specific requirement in release acceptance. | spacing.html:354; original audit #s05-p2 | Label/helper/error/group/list/toolbar/empty/wrapped spacing and scrim/content padding have relationship rules. Current: foundation-contract.json; spacing.html#implementation-contract. | Partial
S06 | Spacing | Implemented | P1 | Visual density not separated from hit-area/separation/text constraints. | Define independent interactive bounds/readability and compact/comfortable role maps. | Source/documentation fix present; include this specific requirement in release acceptance. | spacing.html:258; original audit #s06-p1 | Density is separated from glyph/control/target size; target editor enforces a 44px minimum. Current: foundation-runtime.js; spacing.html#implementation-contract. | Open
S07 | Spacing | Implemented | P2 | Implementation contradicts rule; responsive/logical/native spacing lacks explicit policy. | Audit literals; use semantic tokens; document approved fluid structural/logical/native rules. | Source/documentation fix present; include this specific requirement in release acceptance. | experience.css:22; original audit #s07-p2 | Logical gutters and documented fluid/native exceptions distinguish token adoption from renderer-specific units. Current: foundation.css; spacing.html#implementation-contract. | Partial
S08 | Spacing | Implemented | P1 | Numbers travel without relationship constraints. | Export typed scale, semantic relations, density/platform variants and precedence/rules. | Source/documentation fix present; include this specific requirement in release acceptance. | spacing.js:21; original audit #s08-p1 | Current values, relationship aliases, composition and unit rules travel in Markdown and JSON. Current: foundation-runtime.js; spacing.html#implementation-contract. | Open
R01 | Radius | Implemented | P1 | AI mandates fixed defaults while chosen philosophy changes actual tokens. | Generate active component defaults from philosophy; distinguish base versus effective mapping. | Source/documentation fix present; include this specific requirement in release acceptance. | shell.js:135; original audit #r01-p1 | Chosen philosophy resolves semantic defaults; prompts carry the active mappings instead of fixed seed rules. Current: foundation-model.js; radius.html#implementation-contract. | Open
R02 | Radius | Implemented | P1 | Numeric names stop meaning numbers; incomplete adoption and duplicate mappings drift. | Keep primitives immutable; remap semantic control/card/overlay aliases from one source; audit consumers. | Source/documentation fix present; include this specific requirement in release acceptance. | shell.js:142; original audit #r02-p1 | Numeric radius primitives stay numeric; effective role aliases change with philosophy. Current: tests/foundation-model.test.cjs; radius.html#implementation-contract. | Open
R03 | Radius | Implemented | P2 | Core headline range versus available scale versus role exceptions undefined. | Define core versus full scale and exact allowed/default role intersections. | Source/documentation fix present; include this specific requirement in release acceptance. | radius.html:255; original audit #r03-p2 | Role permissions and pill/circle/attached/native exceptions are explicit in the generated contract. Current: foundation-contract.json; radius.html#implementation-contract. | Partial
R04 | Radius | Implemented | P2 | Contour-following versus independent child implied; borders/asymmetric insets/radii omitted. | Scope formula to contour surfaces, account for borders/insets, illustrate independent controls. | Source/documentation fix present; include this specific requirement in release acceptance. | radius.html:469; original audit #r04-p2 | Contour cap subtracts border plus padding; asymmetric insets and independent child controls are explained. Current: radius.html; radius.html#implementation-contract. | Partial
R05 | Radius | Implemented | P2 | No consolidated attached/full-screen/pill/circle/responsive rules. | Define floating/attached/full-screen/pill/circle semantic variants with per-edge rules. | Source/documentation fix present; include this specific requirement in release acceptance. | radius.html:379; original audit #r05-p2 | Attached, full-screen, pill, circle and responsive radius rules are consolidated. Current: foundation-contract.json; radius.html#implementation-contract. | Implemented
R06 | Radius | Implemented | P2 | No radius invariance across focus/error/selected or overflow-focus clipping guidance. | Keep ordinary state geometry stable; define outlines/overflow/hit areas and intentional transitions. | Source/documentation fix present; include this specific requirement in release acceptance. | radius.html:367; original audit #r06-p2 | Geometry stays invariant through focus/error/selected states; clipping and focus visibility rules are explicit. Current: foundation-contract.json; radius.html#implementation-contract. | Implemented
R07 | Radius | Implemented | P1 | Actual remapping and required role constraints absent. | Export effective semantic map, primitives and attached/nested rules with provenance. | Source/documentation fix present; include this specific requirement in release acceptance. | radius.js:22; original audit #r07-p1 | Current semantic mappings and nested/attached permissions appear in portable Radius handoff. Current: radius.js; radius.html#implementation-contract. | Open
R08 | Radius | Implemented | P2 | Reset can show Balanced then different philosophy on reload. | Separate project recommendation from global default or choose durable reset policy; show inheritance. | Source/documentation fix present; include this specific requirement in release acceptance. | radius.js:161; original audit #r08-p2 | Reset derives the current project recommendation and persists/restores the same effective philosophy. Current: radius.js; radius.html#implementation-contract. | Implemented
B01 | Borders | Implemented | P1 | Promised per-state configuration unavailable. | Implement validated state properties or label them fixed and narrow claim. | Source/documentation fix present; include this specific requirement in release acceptance. | borders.html:419; original audit #b01-p1 | Base geometry is editable; fixed per-state geometry is accurately labelled with editable state colors. Current: borders.html; borders.html#implementation-contract. | Open
B02 | Borders | Partial | P1 | No strategy accommodates thicker border without shifting; preview changes real width. | Reserve maximum transparent border or use outline/inset; show no-shift implementations. | Measure control geometry through focus/error/selected transitions; no-layout outlines are implemented. | borders.html:520; original audit #b02-p1 | Focus outline is separate from resting boundary and layout; real transition measurement remains pending. Current: foundation.css; borders.html#implementation-contract. | Open
B03 | Borders | Implemented | P1 | Focus+error, selected+hover, loading+disabled and success+focus precedence missing; read-only/required absent. | Define orthogonal layers/precedence and keep focus/messages visible; separate read-only. | Source/documentation fix present; include this specific requirement in release acceptance. | borders.html:412; original audit #b03-p1 | Combined error/focus, selection/hover, loading/disabled, success/focus and read-only/required precedence is defined. Current: foundation-contract.json; borders.html#implementation-contract. | Open
B04 | Borders | Partial | P1 | Guarantee unsupported for custom surfaces/transparency; no forced-color recipe. | Validate composited adjacent pairs/focus; document forced colors and unobscured focus. | Verify composited essential boundaries and unobscured focus in forced colors and custom themes. | borders.html:237; original audit #b04-p1 | Compositing, essential boundary contrast and forced-color focus rules are explicit; rendered evidence pending. Current: foundation-contract.json; borders.html#implementation-contract. | Open
B05 | Borders | Implemented | P2 | Seed identity and effective border/state precedence unclear. | Mark Custom/Based on; export one effective composite and define Default inheritance. | Source/documentation fix present; include this specific requirement in release acceptance. | borders.js:154; original audit #b05-p2 | Preset seeding and current live inheritance/application are correctly described rather than promised future work. Current: borders.html; borders.html#implementation-contract. | Partial
B06 | Borders | Implemented | P2 | Scale/consumer width drift lacks governed exceptions. | Audit widths; preserve justified semantic optical exceptions and migrate drift. | Source/documentation fix present; include this specific requirement in release acceptance. | theme.css:21; original audit #b06-p2 | Approved width exceptions and native hairline recipes are documented with consumers and rationale. Current: foundation-contract.json; borders.html#implementation-contract. | Partial
B07 | Borders | Implemented | P1 | Brand/status changes do not retarget stored borders; no linked/overridden provenance. | Default to semantic aliases; allow explicit detached override; resolve by theme. | Source/documentation fix present; include this specific requirement in release acceptance. | borders.js:455; original audit #b07-p1 | Default semantic state colors follow Brand/status until overridden; alias/override precedence travels in export. Current: foundation-model.js; borders.html#implementation-contract. | Open
B08 | Borders | Implemented | P2 | Logical start/end unavailable; native density/print/forced-color translations absent. | Offer/document inline/block sides and physical exceptions; map native/print; explain dividers. | Source/documentation fix present; include this specific requirement in release acceptance. | borders.js:90; original audit #b08-p2 | Logical start/end sides are editable; native, print and forced-color translations are documented. Current: borders.js; borders.html#implementation-contract. | Partial
B09 | Borders | Implemented | P1 | No component exceptions/signal/precedence application contract. | Export typed aliased composites plus precedence/geometry/accessibility rules. | Source/documentation fix present; include this specific requirement in release acceptance. | borders.js:154; original audit #b09-p1 | Portable border contract includes component exceptions, state precedence, accessibility and directional rules. Current: foundation-contract.json; borders.html#implementation-contract. | Open
H01 | Shadows | Implemented | P1 | Selection does not resolve recipes/components; hierarchy conflicts; copy references absent product picker. | Resolve per-philosophy layers/minimum separation or mark guidance-only; correct context copy. | Source/documentation fix present; include this specific requirement in release acceptance. | shadows.js:33; original audit #h01-p1 | Each philosophy resolves actual recipes; Flat preserves required overlay separation through alternatives. Current: foundation-model.js; shadows.html#implementation-contract. | Open
H02 | Shadows | Implemented | P1 | Page/machine data lacks full offset/blur/spread/color/opacity and bindings; Soft/Expressive promise distinction without recipes. | Expose typed primitive/semantic recipes, layering/inset policy and philosophy mappings. | Source/documentation fix present; include this specific requirement in release acceptance. | shadows.html:240; original audit #h02-p1 | Shadow defaults publish typed offset, blur, spread and color composites; mode mappings import independently. Current: tools/generate_tokens.py; shadows.html#implementation-contract. | Open
H03 | Shadows | Partial | P1 | No theme/custom-dark visibility verification or forced-color/print policy. | Define theme-aware surface/border/backdrop alternatives and validate actual adjacency. | Verify actual custom-dark adjacency, borders/backdrops and forced-color/print fallbacks. | theme.css:158; original audit #h03-p1 | Custom-dark, print and forced-color separation alternatives are documented; rendered adjacency evidence pending. Current: foundation-contract.json; shadows.html#implementation-contract. | Open
H04 | Shadows | Implemented | P1 | No stacking/z-index/portal/clipping/nesting/backdrop/focus ownership contract; shadow magnitude not order. | Define layer scale/overlay manager, nested/portal/clipping rules and responsive behavior. | Source/documentation fix present; include this specific requirement in release acceptance. | shadows.html:281; original audit #h04-p1 | Named layers and portal/nesting/clipping/backdrop/focus ownership rules distinguish elevation from stacking. Current: foundation-contract.json; shadows.html#implementation-contract. | Open
H05 | Shadows | Implemented | P2 | Card variants/defaults conflict; inert cards can gain interactive elevation cues. | Define static bordered/elevated/interactive variants and synchronized state defaults. | Source/documentation fix present; include this specific requirement in release acceptance. | shadows.html:317; original audit #h05-p2 | Pressed example uses XS; static bordered, elevated and interactive cards have distinct recipes. Current: shadows.html; shadows.html#implementation-contract. | Partial
H06 | Shadows | Implemented | P2 | No concrete keyboard/touch/reduced-motion state recipes/performance guidance. | Show focus/selected/pressed with second signals, restrained transitions and touch equivalents. | Source/documentation fix present; include this specific requirement in release acceptance. | shadows.html:168; original audit #h06-p2 | Keyboard/touch interaction, reduced-motion alternatives and shadow performance guidance are concrete. Current: foundation-contract.json; shadows.html#implementation-contract. | Implemented
H07 | Shadows | Implemented | P1 | Handoff lacks resolved recipes and normative/layer rules. | Use complete shared export with effective recipes/modes/semantic/layer guidance. | Source/documentation fix present; include this specific requirement in release acceptance. | shadows.html:372; original audit #h07-p1 | Current shadow recipes, layers and mode/alternative rules travel in Markdown/JSON. Current: foundation-runtime.js; shadows.html#implementation-contract. | Open
I01 | Icons | Implemented | P1 | References lost on navigation/reload; no per-file remove/replace; reset incomplete. | Persist/package authorized manifest/files; expose durability; remove/replace/clear with scoped reset. | Source/documentation fix present; include this specific requirement in release acceptance. | icons.js:149; original audit #i01-p1 | Reference assets persist with per-file removal and complete reset; explicit source/manifest travels in handoff. Current: icons.js; icons.html#implementation-contract. | Open
I02 | Icons | Implemented | P1 | No visible keyboard focus target to open chooser. | Real labelled Choose files button/input; optional drag/drop; announce outcomes/focus restoration. | Source/documentation fix present; include this specific requirement in release acceptance. | icons.html:374; original audit #i02-p1 | Upload dropzone is keyboard reachable with a named activation path and visible focus. Current: icons.js; icons.html#implementation-contract. | Open
I03 | Icons | Partial | P1 | No actual type/size/count/decode/read-error/duplicate limits; SVG normalization undefined. Image embedding alone is not proof of script execution. | Validate files/decode, report per-file failures, deduplicate and normalize approved SVG before inline reuse. | Verify malformed/valid asset decoding and error feedback in a real image engine. References are inert; only reviewed catalog glyphs may be inlined. | icons.js:238; original audit #i03-p1 | Bounded type/size/count, duplicates and read/decode errors preserve recovery; references stay inert images. Current: icons.js; icons.html#implementation-contract. | Open
I04 | Icons | Implemented | P2 | Functional UI and illustrations conflated; unsupported controls/library combinations not signposted. | Separate UI/illustration profiles; disable irrelevant controls and validate compatible libraries. | Source/documentation fix present; include this specific requirement in release acceptance. | icons.html:172; original audit #i04-p2 | UI glyphs and illustration references have separate rules; unsupported source/style controls disable accurately. Current: icons.js; icons.html#implementation-contract. | Partial
I05 | Icons | Implemented | P1 | No canonical named catalog/action mapping/normalization/resolver/import implementation. | Approved named set/source and normalized geometry; resolver/import guidance; label references versus integrations. | Source/documentation fix present; include this specific requirement in release acceptance. | icons.js:115; original audit #i05-p1 | Six licensed Google Material actions have canonical names, directional metadata and an accessible SVG API. Current: icon-catalog.json; icons.html#implementation-contract. | Open
I06 | Icons | Implemented | P1 | No complete decorative SVG/meaningful symbol/control/status/loading semantics examples. | Document hidden decoration, named functional controls, textual status/loading and native equivalents. | Source/documentation fix present; include this specific requirement in release acceptance. | icons.html:309; original audit #i06-p1 | Decorative versus labelled SVG, icon-only controls and status/loading announcements have concrete examples. Current: foundation-model.js; icons.html#implementation-contract. | Open
I07 | Icons | Partial | P1 | Glyph versus hit area conflated; optical bounds/stroke scaling/clipping undefined. | Separate glyph/grid/hit tokens; actual-size optical/stroke normalization. | Verify actual-size optical bounds, stroke scaling, clipping and hit areas across styles/devices. | icons.html:270; original audit #i07-p1 | Glyph size, viewBox/stroke and target size are separate; actual optical/clipping/hit-area acceptance remains open. Current: foundation-contract.json; icons.html#implementation-contract. | Open
I08 | Icons | Implemented | P2 | Icon guide does not specify which mirror/invariant, localized meaning or reduced-motion alternatives. | Publish symbol-specific direction/motion rules, distinguish trends/navigation/physical symbols. | Source/documentation fix present; include this specific requirement in release acceptance. | icons.html:350; original audit #i08-p2 | Directional chevrons mirror in RTL; invariant symbols do not; reduced-motion/localized meaning rules are explicit. Current: foundation-model.js; icons.html#implementation-contract. | Implemented
I09 | Icons | Implemented | P2 | No bounded agent prompt/schema, accepted SVGs/rejection criteria, provenance or verified license/version manifest. | Provide geometric/currentColor/name/semantic constraints, human review and approved source manifest. | Source/documentation fix present; include this specific requirement in release acceptance. | icons.html:168; original audit #i09-p2 | Catalog license/provenance and agent constraints define accepted geometry and reviewed versus inert references. Current: foundation-contract.json; icons.html#implementation-contract. | Partial
I10 | Icons | Implemented | P1 | No assets/state/accessibility/direction/generation contract. | Export asset package/references plus normative state/semantics/direction/generation rules. | Source/documentation fix present; include this specific requirement in release acceptance. | icons.js:72; original audit #i10-p1 | Icon handoff carries sources/assets, state/accessibility/direction and generation constraints. Current: icons.js; icons.html#implementation-contract. | Open
A01 | AI & Agents | Implemented | P1 | Rename rationale/source claim factually unsupported; citations plain text. | Use verified real example or explicitly fictional simulation; link exact evidence and affected diff. | Source/documentation fix present; include this specific requirement in release acceptance. | ai-foundation.html:240; original audit #a01-p1 | Rationale uses honest illustrative source labels and linked references rather than unsupported real research claims. Current: ai-foundation.html; ai-foundation.html#implementation-contract. | Open
A02 | AI & Agents | Implemented | P1 | Claims applied without mutation; decline conflated with failure; undo no actual recorded operation. | Label simulation; separate decision/execution; neutral decline; define operation and undo scope. | Source/documentation fix present; include this specific requirement in release acceptance. | ai-foundation.js:24; original audit #a02-p1 | Local approval/decline/Undo reflects recorded decision state; decline is neutral and is not execution failure. Current: ai-foundation.js; ai-foundation.html#implementation-contract. | Open
A03 | AI & Agents | Implemented | P1 | No validation/queue/running/partial/success/failure/cancel/expired/undo-failed lifecycle; retry/idempotency/stale handling missing. | Define lifecycle/transitions/actions/progress/retry/cancel/compensation, distinguish local/external effects. | Source/documentation fix present; include this specific requirement in release acceptance. | ai-foundation.html:216; original audit #a03-p1 | Validated lifecycle covers queue/run/partial/success/failure/cancel/expiry/undo failure, scope and idempotent retry. Current: agent-model.js; ai-foundation.html#implementation-contract. | Open
A04 | AI & Agents | Implemented | P1 | No threshold/evidence/calibration/unknown state; confidence not equivalent to execution outcome. | Define domain evidence/tiering and unknown; avoid fabricated certainty; separate outcome semantics. | Source/documentation fix present; include this specific requirement in release acceptance. | ai-foundation.html:180; original audit #a04-p1 | Confidence allows unknown, separates evidence/calibration thresholds from execution outcome. Current: foundation-contract.json; ai-foundation.html#implementation-contract. | Open
A05 | AI & Agents | Implemented | P1 | Queue/generating/partial/stop/retry/interruption/timeout/completion/autoscroll/announcements undefined. | Real controlled stream example, preserve partial output, coarse announcements, intentional scroll/retry. | Source/documentation fix present; include this specific requirement in release acceptance. | ai-foundation.html:209; original audit #a05-p1 | Executable stream supports partial output, Stop/Continue, interruption/Retry, cancellation and coarse announcements. Current: ai-foundation.js; ai-foundation.html#implementation-contract. | Open
A06 | AI & Agents | Implemented | P1 | Local/reversible versus external/irreversible, changed-scope consent, expiry/resource impacts unspecified. | Define effect previews/capability-based autonomy and scope; reuse valid authorization, renew only for changed/defined scope. | Source/documentation fix present; include this specific requirement in release acceptance. | ai-foundation.html:223; original audit #a06-p1 | Local versus external effects, approval scope, changed-scope consent, expiry and resource limits are defined. Current: foundation-contract.json; ai-foundation.html#implementation-contract. | Open
A07 | AI & Agents | Implemented | P1 | Outcome announcement/focus recovery incomplete; hypothetical undo timing unspecified. | Announce outcome and restore focus; keyboard-operable undo with defined timing/persistence; neutral decline. | Source/documentation fix present; include this specific requirement in release acceptance. | ai-foundation.js:15; original audit #a07-p1 | Decision/stream outcomes have named status and focus recovery; pending/undo timing is documented. Current: ai-foundation.js; ai-foundation.html#implementation-contract. | Open
A08 | AI & Agents | Implemented | P1 | No authoritative token resolution/conflict/missing-data/schema/verification contract; external evidence not distinguished from instructions. | Publish trusted-source precedence, capabilities, scope, output/provenance schemas and validation requirements; treat evidence as data. | Source/documentation fix present; include this specific requirement in release acceptance. | ai-foundation.html:249; original audit #a08-p1 | Agent input/output contract defines authority, trusted evidence, schema, missing data, capabilities and verification. Current: foundation-contract.json; ai-foundation.html#implementation-contract. | Open
A09 | AI & Agents | Implemented | P1 | Defining agent guidance cannot travel through complete handoff. | Include AI rules/contracts/tokens in manifest/export and make intentional omission visible. | Source/documentation fix present; include this specific requirement in release acceptance. | experience.js:220; original audit #a09-p1 | AI is included in catalog, nine-section readiness and complete portable Foundation handoff. Current: project-model.js; ai-foundation.html#implementation-contract. | Partial
A10 | AI & Agents | Implemented | P2 | No mixed human/AI authorship, source history, multi-agent contribution, redacted/missing/private evidence or verification rules. | Define provenance/version/tool/human-review/edit/redaction fields and progressive disclosure; require supportable evidence. | Source/documentation fix present; include this specific requirement in release acceptance. | ai-foundation.html:176; original audit #a10-p2 | Provenance/privacy rules cover mixed authorship, tools/review history, private/missing sources and retention. Current: foundation-contract.json; ai-foundation.html#implementation-contract. | Partial